PAYBACKER

Master Launch Plan

The automated marketing playbook for Paybacker LTD

From Yapily-approved to first 1,000 paying subscribers

| Version | v1.0 — 18 April 2026 |
| --- | --- |
| Owner | Paul Airey, Founder |
| Launch trigger | Yapily Open Banking integration approved |
| Planning horizon | 60-day launch sprint + 90-day scale |
| Budget cap | £2,000/month running costs (incl. Yapily £600, Switchcraft £1,000) |
| Companion assets | 21 template files at docs/marketing/templates/ |

# Executive Summary

The ask: Launch Paybacker with the highest impact possible while keeping cash-burn near zero, maximising AI and automation everywhere it displaces a marketing hire.

The answer: A founder-led, AI-assisted launch that leans into Paul's personal narrative, UGC produced by paid micro-influencers (not written content), community credibility in UK consumer spaces, and a single paid channel (Google) that compounds into everything else.

## The one-page plan

| Lever | Who does it | Cost | Why |
| --- | --- | --- | --- |
| Founder PR (Katie Morley, HARO, Martin Lewis) | Paul + press cron | £0 | Warmest intros = lowest CAC |
| UGC creator programme (JoinBrands + Collabstr) | Paul briefs, creators film, Paybacker reposts | £500-1,500/mo | 1 video = 30 static ad creatives |
| Owned social (30 seed ideas) | Paul films, content cron drafts captions | £5/mo API | Free reach + algorithmic upside |
| Community seeding (FB Groups, niche subreddits) | Paul, manual, value-first | £0 | Long-term trust. No Reddit promo. |
| Paid Google Search | Paul or Blaze.ai | £450-900/mo | Highest-intent channel |
| Paid Meta retargeting only | Auto via pixel + Blaze.ai | £300-450/mo | Recover visitors; not cold scale |
| Product Hunt + Show HN | Paul, twice, pre-planned | £0 | 10-40k visitors in 24 hours each |
| Partnerships (banks, rewards, charities) | Paul direct outreach | £0 | Distribution at the tail |

The single largest bet Katie Morley. A single warm national-press placement from her Telegraph column drives more high-intent UK signups than every paid channel combined in the first 8 weeks. Paul sends the warm reconnection email on Day 1, personally.

## 60-day success criteria

| Metric | Week 2 | Week 4 | Week 8 |
| --- | --- | --- | --- |
| Weekly unique visitors | 500 | 2,000 | 5,000 |
| Weekly signups | 40 | 150 | 400 |
| Signup → first letter activation | 55% | 60% | 65% |
| Weekly paid conversions | 2 | 15 | 45 |
| MRR | £20 | £100 | £400 |
| Blended CAC | £15 | £12 | £8 |
| UGC videos produced | 2 | 8 | 20 |
| Press placements | 0 | 1 | 3 |

Trend >30% below any row for two consecutive weeks = stop, diagnose, re-plan. See Part 6: Escalation rules.

# Part 1 — Strategic Context

## 1.1 The thesis

Core thesis (memorise this) "I'm tired of people — including myself — being ripped off by companies, where normal working people can't realistically pay solicitors to represent them for the day-to-day injustices that happen constantly. This needs to change. That's why I built Paybacker."

Every piece of Paybacker communication — the website copy, the cold press email, the 12-word TikTok hook, the UGC brief — is a compression of this thesis. The emotional backbone is never "subscription tracker with AI." It is always: it is now as easy for a normal person to fight back as it is for a company to rip them off.

→ Template: Three founder-story lengths (A, B, C) for every context  [docs/marketing/templates/founder-story-three-lengths.md]

## 1.2 Who this is for

UK consumers, 25-50, tech-comfortable, time-poor, who notice that a lot of their money goes sideways each month but don't have the time, money, or legal knowledge to push back. Not high-net-worth. Not students. The 70% of UK working adults who earn between £28k and £80k and lose an estimated £1,000+ a year to administrative passivity they cannot personally fix.

Secondary persona (month 3+): small landlords, self-employed contractors, and older consumers experiencing post-pandemic "ripped off in every direction" fatigue.

## 1.3 What we keep, kill, and reshape

From the v1 marketing proposal (Favoured): the strategic framing is strong — founder-led, narrative-first, UK-specific law as moat. We keep that framing entirely. We kill the £20k+/mo agency retainer. We reshape the production pipeline to in-house + UGC creators + crons.

From the v2 Claude web launch plan: the 12-section structure (thesis, tactics, UGC programme, PR, HN/PH, paid ads) is the backbone we keep. We kill Reddit user-posting (banned before — see §3.4). We reshape Meta into retargeting-only during launch, not cold acquisition.

From the existing in-house marketing plan: the 4 creative routes (Legal Eagle, Subscription Audit, Pocket Agent POV, Bill Battle), 60 seed post ideas, and Drew's 4 email flows all remain current and usable. The budget column in Table 13 is the one we reshape — this plan operates at ~£1,250/mo marketing including ads, not the previously-planned £7k.

# Part 2 — The Launch Sprint

60 days from Yapily approval to "we are a real, compounding, revenue-generating UK consumer brand."

## 2.1 Launch trigger

T-0 = the day Yapily confirms Open Banking integration approved. Until then this plan is in dress rehearsal: assets built, crons coded, drafts queued, but nothing sent. On approval, Paul flips a single env var (LAUNCH_LIVE=true), which releases the scheduled first sends across all channels.

## 2.2 Week-by-week

### Week 0 — Dress rehearsal (pre-Yapily)

- Complete all template-driven assets: press emails, UGC brief, ad creative library, 30 seed videos filmed and ready, cron routes deployed but kill-switched.

- Seed content_ideas table (30 rows) and marketing_angles table from templates.

- Verify Meta Business Manager, domain verification, Pixel + CAPI, Google Ads conversions set up.

- Draft Katie Morley email, review factual details, queue to send on Day 1.

- Sign up for JoinBrands; post first 3 UGC jobs (paused, ready to go-live).

- Sign up Blaze.ai Pro trial; ensure it connects to Meta + Google Ads accounts.

### Week 1 — Ignition

- Day 1: send Katie Morley warm email (Paul, personally). Send 5 cold press pitches (Guardian Money, Telegraph Money, BBC Radio Money, Yahoo UK, Which?).

- Day 1: publish site-wide go-live (free tier open, Stripe live, waitlist disabled).

- Day 1: Paul posts on personal LinkedIn + X: "I built Paybacker." Founder-story version B.

- Day 2-3: release 3 TikToks from seed list, Reels mirrors, first paid Google Search campaign live at £15/day.

- Day 4-5: first UGC creator briefs sent via JoinBrands. Expect first deliveries Day 11-14.

- Day 6-7: review KPI dashboard. First Friday 30-min review.

### Week 2-3 — First press placement window

- Daily press cron delivers 3-10 HARO/Qwoted drafts; Paul reviews + sends 3-5 per day.

- Second wave of cold pitches to 10 more journalists, referencing Week 1 traction if any.

- First 2 UGC deliveries go live as Paybacker reposts + Meta retargeting ads.

- First Facebook-group engagement session (Paul, 30 min, 3 groups).

- Blaze.ai takes over daily ad optimisation for Google + Meta retargeting.

### Week 4 — Product Hunt launch

- Tuesday or Wednesday launch. Paul clears the day; comments for 12 hours straight.

- Pre-warmed supporter list (15-30 real people) nudged at 08:01 UK.

- Expect 2-5k site visitors and 50-200 signups on the day.

→ Template: Product Hunt launch checklist  [docs/marketing/templates/product-hunt-checklist.md]

### Week 5 — Consolidation

- Ramp UGC volume to 2-3 creators/week briefed.

- First partnership outreach (3-5 challenger banks, rewards platforms, Citizens Advice).

- Launch second paid Google campaign (next-highest intent keyword cluster).

- Review ad creative; kill bottom 3, double top 1.

### Week 6 — Show HN launch

- Tuesday morning UK. Show HN post goes live.

- Paul clears 4 hours; answers every comment within 20 minutes for first 4.

- Expected 10-40k visitors in 24 hours; 200-800 signups.

→ Template: Show HN draft  [docs/marketing/templates/hacker-news-show-hn-draft.md]

### Weeks 7-8 — Sustain and scale

- Meta retargeting scaled to £20/day if CAC holds under £10.

- Lookalike cold audience test launched (1-3% of paid subscribers).

- Third wave of press (follow-ups on cold pitches, new angles).

- Martin Lewis pitch window opens only if case-study dataset exceeds £15,000 recovered.

# Part 3 — Channel Playbooks

Every playbook in this section has a dedicated template file. The body here is the strategic summary; the template is the operational artefact.

## 3.1 Founder-led PR and press

Why this is the #1 channel: one national press placement in a UK consumer column = the cost-equivalent of 8-12 weeks of paid Google at current CAC levels. Founder warmth + FCA-authorised credibility + live case studies is the package journalists want.

### Tier 1: Katie Morley (warm reconnect)

Paul met Katie Morley — now Telegraph Money consumer-champion columnist — in 2007 as students at neighbouring University of London halls. The warmth is real. The Day 1 send is a single long-shot personal email that lightly echoes their shared history and pivots onto the Paybacker thesis via 2007-vs-2026 London finance. No pressure, low-stakes close.

Critical guardrails: Paul sends personally, from his own inbox. Cowork NEVER sends this. The email does not ask for coverage — it opens the door. Email 2 (the actual pitch) only sends if Email 1 gets a warm reply.

→ Template: Katie Morley warm reconnect email (v2)  [docs/marketing/templates/katie-morley-email-v2.md]

### Tier 2: Cold master pitch

Every other consumer/money/tech journalist receives a variant of the cold master pitch. 15-18 journalists targeted in Week 1, another 15 in Week 2. Each email: one hook, one founder sentence, three concrete editorial offers. Never "let's chat."

→ Template: Cold master pitch  [docs/marketing/templates/master-pr-pitch.md]

### Tier 3: Martin Lewis (special-case, not at launch)

One shot. Not at launch — wait until 50+ real case studies and £15,000+ recovery data exists. Pitch is a gift: one specific niche UK consumer-law finding, hard numbers, no ask.

→ Template: Martin Lewis dedicated pitch  [docs/marketing/templates/martin-lewis-pitch.md]

### Tier 4: HARO / Qwoted / ResponseSource

The daily compounding play. Journalist source-requests land in the press cron daily; Paul reviews drafts and sends 3-5 per day. One placement per month is a success; a good quarter is 5-10 cumulative. Expected CAC: £2-4/signup from a placement.

→ Template: HARO / Qwoted response templates and angle library  [docs/marketing/templates/haro-qwoted-responses.md]

## 3.2 UGC creator programme

Platform decision: JoinBrands primary (250k+ UK creators, pay-per-video £80-500, no monthly subscription), Collabstr backup (particularly for higher-follower TikTok creators). Twirl used only if a specific UK finance creator surfaces there and is not findable on JoinBrands.

Why UGC not agency video: a £250 UGC video from a real UK micro-influencer outperforms a £2,500 agency-produced ad by 2-4x on Meta and TikTok. The "real person fighting their own fight" feel cannot be faked.

Target volume: 3-5 completed videos per month. Paybacker reposts on owned channels within 48 hours of approval. Every video is cut to a 10-second ad variant for paid retargeting.

### The programme stack

→ Template: UGC creator brief (attached to every job)  [docs/marketing/templates/ugc-creator-brief.md]

→ Template: Direct outreach template (for spotted creators outside platforms)  [docs/marketing/templates/ugc-outreach-template.md]

→ Template: Three starter scripts (A: parking fine, B: mid-contract hike, C: founder)  [docs/marketing/templates/ugc-scripts-A-B-C.md]

## 3.3 Owned organic social

Paybacker-owned channels: TikTok (@paybacker.co.uk), Instagram, Facebook Page, X (@PaybackerUK), LinkedIn company page. The "always on" content engine: 3 videos/week during launch, 2/week sustained.

Production model: Paul films on iPhone (15-min/video), the content cron drafts captions overnight, Paul approves in 5 min on the admin dashboard, Late API publishes cross-platform at optimal times.

→ Template: 30 seed video ideas (4 pillars: Injustice, Product, Education, Founder)  [docs/marketing/templates/tiktok-reels-30-seed-ideas.md]

→ Template: Content generator cron (daily 7am)  [docs/marketing/templates/cron-content-generator.md]

## 3.4 Community seeding

Reddit constraint (explicit Paul directive) We cannot post as a user promoting the product on Reddit. Previous attempts led to bans. This plan's Reddit approach is value-first comments only — answering real consumer-rights questions as Paul-the-founder from a transparent account, with no link unless directly asked. Top-level promotional threads never happen.

→ Template: Reddit value-first strategy and subreddit targets  [docs/marketing/templates/reddit-value-comments.md]

Facebook Groups are the higher-ROI community play. 10+ UK consumer/renter/money groups with 10k-100k members and looser moderation than Reddit. Same principle: Paul answers questions helpfully, product link mentioned only when asked.

→ Template: Facebook Groups playbook and target list  [docs/marketing/templates/facebook-groups-playbook.md]

## 3.5 Paid acquisition

Budget discipline: £450-900/mo Google Search (primary), £300-450/mo Meta retargeting (secondary), £0 on Meta cold acquisition until week 6+ when lookalike audiences have data to work with. Never TikTok paid during launch — the owned TikTok channel + UGC creator posts cover that surface.

### Google Ads — the primary paid channel

8 single-theme campaigns, each targeting a specific consumer-rights problem: parking fines, energy disputes, broadband price rises, flight delay, council tax, subscription cancellation, debt collection, brand-defence. Each lands on a dedicated SEO page.

→ Template: Google Ads keyword list, ad copy, campaign structure  [docs/marketing/templates/google-ads-keyword-list.md]

### Meta — retargeting only during launch

Meta Pixel + Conversions API installed server-side to track every signup/purchase event. Three retargeting audiences (website visitors, free-tier users, cart abandoners). Cold acquisition via lookalike only unlocks in month 2.

→ Template: Meta retargeting setup  [docs/marketing/templates/meta-retargeting-setup.md]

### Ad creative pipeline

All image and video generation goes through fal.ai only, per CLAUDE.md architecture rule. 30+ prompts pre-written for 3 image pillars (Injustice, Product, Founder). Text overlays and CTAs added in post via Canva — never generated, never hallucinated.

→ Template: fal.ai prompt library + brand spec  [docs/marketing/templates/ad-creative-prompts.md]

## 3.6 Launch events

Two planned high-intensity events during the 60-day sprint: Product Hunt (Week 4) and Show HN (Week 6). Both free-to-enter, both capable of 2-40k visitors in 24 hours, both zero-cost aside from Paul's full-day attention on the day.

→ Template: Product Hunt launch checklist  [docs/marketing/templates/product-hunt-checklist.md]

→ Template: Show HN submission draft + pre-canned answers  [docs/marketing/templates/hacker-news-show-hn-draft.md]

## 3.7 Partnerships

Month 2-3 priority. Five partner types: challenger banks, cashback platforms, Citizens Advice/charity, price-comparison sites, insurance brokers. Each gets a tailored hook from the partnership template.

→ Template: Partnership pitch template + partner-type hooks  [docs/marketing/templates/partnership-pitch.md]

# Part 4 — Automation Stack

The premise of this plan: nearly-zero marketing budget, so every role a salaried marketing hire would do is automated or compressed into Paul-reviews-drafts-on-phone.

## 4.1 Existing infrastructure (already live)

| Service | Role | Status | Monthly cost |
| --- | --- | --- | --- |
| fal.ai | All image + video generation | Live | £15-30 (usage) |
| Late API (getlate.dev) | Cross-platform social posting | Live | £25-50 |
| Resend | Transactional + marketing email | Live | £15 |
| PostHog | Product analytics + conversion tracking | Live | £0 (free tier fits) |
| Perplexity API | Real-time research (Leo/Nico agents) | Key held | £0 (usage-based) |
| Meta Pixel + CAPI | Ad tracking (pending install) | Partial | £0 |
| Google Ads | Paid search | Live | Spend ~£450-900 |

## 4.2 New crons to add

Three new scheduled routes that replace the dormant Casey/Taylor/Pippa executive agents with lightweight, auditable, single-purpose workers:

| Cron | Schedule | What it does | Template |
| --- | --- | --- | --- |
| /api/cron/generate-content | Daily 07:00 | Drafts 3 social captions + images for Paul to approve | cron-content-generator.md |
| /api/cron/ugc-outreach | Mon/Wed/Fri 10:00 | Sources 10 creators, drafts personalised DMs, queues for manual send | cron-ugc-outreach.md |
| /api/cron/press-outreach | Daily 09:00 (weekdays) | Pulls HARO/Qwoted queries, drafts responses, drafts follow-ups | cron-journalist-followup.md |

Critical rule: every cron drafts only — Paul (or approved admin) reviews and sends. Never auto-send DMs, emails, or press responses. Relationships live or die by sender authenticity.

## 4.3 Ad management

Decision: Blaze.ai Pro ($45/mo) for the 60-day launch sprint. Rationale: during launch, Paul cannot spend 2 hours/day optimising Meta + Google simultaneously; Blaze.ai handles creative iteration and bid management in one dashboard. At month 3, replace with an in-house Cowork-driven admin dashboard extension that reads the same APIs — removes the subscription, keeps the control.

What Blaze.ai does: connect both Meta and Google Ads accounts via OAuth, let Claude-inside-Blaze iterate ad creative (using fal.ai outputs), run multivariate testing, flag underperforming ad sets. Pauses ads automatically above defined CPA thresholds. One dashboard replaces three agency tools.

What it does NOT replace: Paul's weekly Friday review. The KPI dashboard is the truth-source; Blaze is the execution layer.

## 4.4 Supabase tables and keys to add

Migration additions (all CREATE TABLE IF NOT EXISTS, per CLAUDE.md rule — no DROP/ALTER destructive):

- content_ideas (seeded from tiktok-reels-30-seed-ideas.md)

- marketing_angles (seeded from haro-qwoted-responses.md angle library)

- ugc_creators (schema defined in ugc-outreach-template.md)

- press_outreach (schema defined in cron-journalist-followup.md)

- partnership_pipeline (journalist_name, company, stage, last_touch_at, status)

API keys to acquire (one-time setup):

- APIFY_TOKEN — for TikTok creator scraping (free tier)

- HUNTER_IO_KEY — for journalist/partner email verification (£15/mo starter)

- BLAZE_API_KEY — for ad management during launch (included in $45/mo Blaze Pro)

- JOINBRANDS_API_KEY — optional; manual job posting works without (free to create account)

## 4.5 Admin UI pages to build

Each is a simple Next.js admin page; total build time estimated 2-3 working days:

| Page | Purpose | Priority |
| --- | --- | --- |
| /admin/content-drafts | Approve/edit/reject daily content drafts | Week 0 blocker |
| /admin/ugc-outreach | Review cron-drafted DMs; copy-paste-send | Week 0 blocker |
| /admin/press-outreach | Review query drafts; copy-paste-send | Week 0 blocker |
| /admin/kpi-weekly | The Friday 30-min dashboard | Week 1 blocker |
| /admin/ad-performance | Cross-platform ad CPA view (Blaze + direct) | Week 2 nice-to-have |

# Part 5 — Budget and Economics

## 5.1 Running costs — the fixed base

| Line | Monthly cost | Notes |
| --- | --- | --- |
| Yapily (Open Banking AISP) | £600 | Core feature dependency |
| Switchcraft (planned) | £1,000 | Comparison/switching API — coming soon |
| Vercel Pro + Supabase + Resend + PostHog | £50 | Stack overhead |
| Anthropic API (agents + complaints) | £80-150 | Usage-scales-with-users |
| fal.ai (image + video) | £25-40 | Usage-scales-with-content |
| Late API (social posting) | £25-50 | All platforms via one integration |
| Other APIs (Perplexity, Apify, Hunter.io) | £40 | Sparse usage |
| Blaze.ai Pro (launch-only, 60 days) | £35 | Replaced month 3 |
| TOTAL fixed monthly base | £1,855-1,970 | Near £2,000 ceiling |

## 5.2 Marketing budget

The marketing budget is £750-1,250/month during the launch This sits on top of the fixed base. Total business-running cost is ~£2,000/mo base + ~£1,000/mo marketing ≈ £3,000/mo all-in. Every pound of that is accounted for against explicit goal metrics.

| Channel | Week 1-2 | Week 3-4 | Week 5-8 | Month 3+ |
| --- | --- | --- | --- | --- |
| Google Ads | £210 | £420 | £630 | Scale to CAC |
| Meta retargeting | £0 | £140 | £210 | Scale to CAC |
| UGC creator payments | £300 | £400 | £600 | £800 |
| Hunter.io (email verif) | £15 | £15 | £15 | £15 |
| Blaze.ai Pro | £35 | £35 | £35 | Discontinued |
| ResponseSource (if taken) | £0 | £0 | £50 | £50 |
| WEEKLY marketing total | £140 | £250 | £385 | Variable |
| Monthly run-rate | £560 | £1,000 | £1,540 | £1,500-2,000 |

## 5.3 Unit economics targets

Paybacker is subscription-led. The LTV/CAC math matters more than top-line signups.

| Metric | Assumption | Target |
| --- | --- | --- |
| ARPU (Essential) | £4.99/mo | — |
| ARPU (Pro) | £9.99/mo | — |
| Blended ARPU | £5.80/mo | Assumes 70/30 split |
| Churn (annual, year 1) | ~30% | High for SaaS; low for a utility product |
| Expected LTV (gross) | £96 | £5.80 × 16.7 months avg |
| LTV after Stripe + support cost | ~£78 | Net |
| CAC ceiling (1:3 ratio) | £26 | Walk-away line |
| CAC target | £8 | Launch goal; enables 9-10x payback |
| CAC during first 30 days | £12-18 | Acceptable while learning |

## 5.4 Break-even math

Monthly break-even: at £3,000/mo cost base and £5.80 blended ARPU, break-even = 517 active paying subscribers. Current waitlist + launch traction target: 400 MRR-contributing subscribers by end of Week 8, 600+ by end of month 3.

Runway implication: every paying customer earned in the 60-day sprint adds roughly £78 of net LTV. The launch sprint's target (45 paid conversions/week by Week 8) implies £3,500 of LTV added per week — a meaningful compounding asset.

# Part 6 — Measurement and Review

## 6.1 The 12 numbers

One dashboard, read every Friday morning, 30 minutes.

→ Template: Full KPI dashboard spec + 5-question review format  [docs/marketing/templates/kpi-weekly-review.md]

| Group | Number |
| --- | --- |
| Acquisition | 1. Weekly unique visitors (PostHog) |
|  | 2. Weekly signups (Supabase auth.users) |
|  | 3. Signups by source (organic / Google / Meta / TikTok / referral / direct) |
| Activation | 4. % of signups who generate first letter within 24h |
|  | 5. % of signups who connect a bank within 7 days |
|  | 6. Letters generated this week |
| Revenue | 7. Weekly paid conversions (Stripe) |
|  | 8. MRR delta this week |
|  | 9. Cancellations / churn this week |
| Efficiency | 10. Blended CAC |
|  | 11. Top 3 and bottom 3 ad creatives by CPA |
|  | 12. Content drafts approved / generated this week |

## 6.2 The five questions

Paul answers five questions every Friday. Answers go to business_log and shared-context/handoff-notes.md.

- What's the #1 thing that went right this week? (specific number)

- What's the #1 thing that went wrong this week? (specific number)

- Cheapest paying customer channel this week? Can we do more of that?

- Biggest-burn channel this week? Pause or iterate?

- What's the ONE bet for next week?

## 6.3 Escalation rules

Stop the sprint and re-plan if any of these hold for 2 consecutive weeks:

- Blended CAC > £20

- Signup → paid conversion < 0.3%

- Letter generation failure rate > 5%

- Any single paid channel > 70% of acquisition AND that channel is paid (platform-dependency risk)

## 6.4 Automatic alerts

Resend-triggered emails to Paul when any threshold trips:

- Daily ad spend > £50 (email + SMS)

- Weekly blended CAC > £20

- Any /api/cron/* returns non-2xx

- Content drafts backlog > 10 pending

- UGC outreach backlog > 15 pending_send

# Part 7 — Paul's Execution Checklist

The day-by-day "what do I actually do" list for the launch sprint. Everything not on this list is automated, delegated, or optional.

## Before launch (Week 0)

- Confirm Yapily approval ETA with Yapily account manager.

- Deploy 3 crons (content, ugc-outreach, press-outreach) behind kill-switches.

- Run migrations for new tables (content_ideas, marketing_angles, ugc_creators, press_outreach, partnership_pipeline).

- Build 5 admin UI pages (content-drafts, ugc-outreach, press-outreach, kpi-weekly, ad-performance).

- Seed content_ideas and marketing_angles from template files.

- Sign up: JoinBrands (free), Collabstr (free), Blaze.ai Pro trial, Apify (free), Hunter.io (£15/mo).

- Film 8 starter TikToks (pillars 1, 2 mainly) — stockpile before launch.

- Draft Katie Morley email; review facts, spelling, factual details about 2007; save as drafts/ready-to-send.

- Write cold press list: 18 UK journalists, verified emails via Hunter.io, one personalised hook per name.

- Verify Meta Business Manager; install Meta Pixel + CAPI server-side.

## Day 1 (Yapily approved)

- 07:00 — flip LAUNCH_LIVE=true env var in Vercel.

- 08:30 — send Katie Morley email (personally, from Paul's inbox).

- 09:00 — send 5 tier-1 cold press pitches.

- 10:00 — post personal LinkedIn + X thread: "I built Paybacker" (Founder Story B).

- 11:00 — enable Google Ads campaigns 1-3.

- 14:00 — post 3 TikToks (first 3 from seed list) via Late API.

- 15:00 — post first 3 UGC creator jobs on JoinBrands.

- 17:00 — review day-one analytics. Screenshot for record.

## Daily cadence (recurring)

| Time | Duration | What |
| --- | --- | --- |
| 07:30-07:45 | 15 min | Review overnight content-draft queue; approve 2-3 |
| 09:00-09:15 | 15 min | Review press-draft queue; send 3-5 HARO/Qwoted responses |
| 10:00-10:15 (M/W/F) | 15 min | Review UGC outreach drafts; send 5-8 DMs/emails |
| 19:00-19:30 (M/W/F) | 30 min | Film one TikTok using a seed idea |
| Ad-hoc | 10 min | Reply to any journalist / partner / press email within 2h |

## Weekly cadence

- Friday 10:00-10:30 — KPI review (see Part 6)

- Friday 10:30-11:00 — Update shared-context/handoff-notes.md; commit and push

- Sunday 19:00-19:45 — Facebook Groups engagement (2-3 groups, 5-8 thoughtful replies)

- Sunday 20:00-20:30 — Reddit engagement (3 subs, 3-5 value replies)

## Weekly bets to plan for

Week-specific single-focus bets that compound:

- Week 1: Katie Morley warm reply (the highest-leverage Day-1 action).

- Week 2: First HARO/Qwoted placement.

- Week 3: First UGC deliveries live; first paid Meta retargeting sequence firing.

- Week 4: Product Hunt launch day.

- Week 5: First partnership conversation booked.

- Week 6: Show HN launch.

- Week 7: First lookalike cold Meta campaign live.

- Week 8: Martin Lewis pitch window opens (if dataset ≥ £15k recovered).

# Appendix

## A. Templates index

All templates live at docs/marketing/templates/. Each is self-contained and revision-able without touching the master plan.

| Category | Template |
| --- | --- |
| Narrative backbone | founder-story-three-lengths.md |
| Press — warm | katie-morley-email-v2.md |
| Press — cold | master-pr-pitch.md |
| Press — special | martin-lewis-pitch.md |
| Press — query response | haro-qwoted-responses.md |
| UGC — brief | ugc-creator-brief.md |
| UGC — outreach | ugc-outreach-template.md |
| UGC — scripts | ugc-scripts-A-B-C.md |
| Owned social — ideas | tiktok-reels-30-seed-ideas.md |
| Community — FB | facebook-groups-playbook.md |
| Community — Reddit | reddit-value-comments.md |
| Launch events — PH | product-hunt-checklist.md |
| Launch events — HN | hacker-news-show-hn-draft.md |
| Partnerships | partnership-pitch.md |
| Paid — Google | google-ads-keyword-list.md |
| Paid — Meta | meta-retargeting-setup.md |
| Paid — creative | ad-creative-prompts.md |
| Automation — content cron | cron-content-generator.md |
| Automation — UGC cron | cron-ugc-outreach.md |
| Automation — press cron | cron-journalist-followup.md |
| Review | kpi-weekly-review.md |

## B. Risk register

| Risk | Probability | Mitigation |
| --- | --- | --- |
| Yapily approval delayed >30 days | Medium | Dry-run sprint in dev; launch triggers are env-gated. Prepare alternate demo flow on test data. |
| Meta ad account flagged / limited | Medium | Run through verified Business Manager with Companies House evidence. Have fresh account on reserve. |
| Google Ads disapproval for "legal claims" policy | Medium | Use neutral ad copy; avoid "guaranteed refund" language; append Paybacker LTD legal-entity footer. |
| Katie Morley non-reply | High | Treat as baseline. Follow the cold-pitch stream as primary path. No further contact with Katie. |
| UGC creators drop rates / low volume | Low-Medium | Multiple platforms (JoinBrands + Collabstr + direct outreach). Buffer of 15 in pipeline. |
| Negative PR (a product failure goes viral) | Low | Response protocol: Paul replies personally within 2h, offers refund + case-specific help. Transparent post-mortem on own channels. |
| CAC > £20 sustained | Medium | Escalation rule: pause paid spend, double down on press + UGC organic. |
| Legal challenge to specific generated letter | Low-Medium | Letters include "AI-generated, not legal advice" disclaimer in-product. Opinion-based not fact-based framing. User reviews before sending. |
| FCA / ICO compliance flag | Low | Regular regulatory review; Yapily handles AISP regulated activity; ICO registration current. |

## C. Do-not-do list

Mistakes from prior attempts and explicit Paul directives. These are non-negotiable.

- Do NOT post as a user on Reddit promoting Paybacker. We've been banned doing this.

- Do NOT auto-send any DM, email, press response, or partnership pitch. Always human-sent after cron-drafts.

- Do NOT integrate directly with OpenAI image gen, Midjourney, Stability — all image/video must go through fal.ai per CLAUDE.md.

- Do NOT integrate directly with Meta/TikTok/LinkedIn posting APIs — use Late API exclusively.

- Do NOT modify complaint_writer or Riley support agent without explicit Paul approval — those two actually serve users.

- Do NOT run Reddit brigade campaigns or upvote rings for Product Hunt / Show HN.

- Do NOT use "Paybacker will save you £1,000/year" claims without real average data to back them.

- Do NOT bid on "Martin Lewis" or "MoneySavingExpert" in Google Ads.

- Do NOT send the Katie Morley email from Cowork. Paul sends personally, from his own inbox.

- Do NOT pitch Martin Lewis before the dataset exceeds £15,000 recovered and 50+ real case studies.

## D. Decision log — key choices in this plan

| Decision | Rationale | Alt considered |
| --- | --- | --- |
| JoinBrands primary UGC platform | 250k UK creators, pay-per-video, no subscription, easy to manage | Twirl (subscription-heavy), Collabstr (backup) |
| Blaze.ai for ad management during launch only | Connects Meta + Google, under £50/mo, replaceable with in-house Cowork extension at month 3 | AdCreative.ai, Madgicx, agency |
| Reddit = value-first comments only, no promotion | Explicit Paul directive — previously banned for promotional posts | Paid Reddit ads (ignored — high fraud, low ICP) |
| Meta = retargeting only during launch | Cold acquisition needs lookalike data we don't have yet | Cold Meta from Day 1 (rejected — wasteful) |
| Google Ads is the primary paid channel | Highest commercial intent per £; existing account healthy | TikTok paid (rejected — better served by owned + UGC) |
| Katie Morley warm email on Day 1 | Single highest-leverage action; reconnection decays fast | Wait until live traction (rejected — the warmth is the asset) |
| Master doc + templates folder structure | Shorter master doc, template files can be updated independently | Single 80-page doc (rejected — friction) |